## Reviews
In production one of the major activity is the review process. As we know that there can be two types of reviews, Group Review or One Person Review. By conducting reviews we can identify the defects or the improvement areas. However, before conducting the review, it has to be appropriately logged. In production we log a review in IPM+. For our learning purposes we will use an excel template but with the same data required to log a review. Below you will find the various attributes required to log a review. You will find that most of the fields have a drop down box, which allows us to select the best option.
Review Name | Review Type | Cycle | Activity Type | Review Date (MM/DD/YY) | Artifact Type | Artifact Name | Artifact Version | Artifact Size | Artifact Unit | Artifact Location
UTP_Apply Review | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_Apply | 0.1 | 6 | Pages | $\ICCI_Bank\Documentation
UTP_Approve Review | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_Aprove | 0.1 | 3 | Pages | $\ICCI_Bank\Documentation
UTP_Approve_Pending_Reject_CardReport | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_Approve_Pending_Reject_CardReport | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_BlockCard | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTTP_BlockCard | 0.1 | 4 | Pages | $\ICCI_Bank\Documentation
UTP_CardDetails | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_CardDetails | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_BlockStatistics | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_BlockStatistics | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_ChooseScheme | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_ChooseScheme | 0.1 | 6 | Pages | $\ICCI_Bank\Documentation
UTP_CustomerLogin | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_CustomerLogin | 0.1 | 4 | Pages | $\ICCI_Bank\Documentation
UTP_HomePages | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_HomePages | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_Login | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_Login | 0.1 | 4 | Pages | $\ICCI_Bank\Documentation
UTP_MakePayment | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_MakePayment | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_OnlineTransactions | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_OnlineTransactions | 0.1 | 4 | Pages | $\ICCI_Bank\Documentation
UTP_Payment | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_Payment | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_Revenuestatistics | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_Revenuestatistics | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_SchemeReport | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_SchemeReport | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_TransactionsStatistics | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_TransactionsStatistics | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
UTP_UnBlock_Card | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_UnBlock_Card | 0.1 | 3 | Pages | $\ICCI_Bank\Documentation
UTP_ViewCardDetails | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_ViewCardDetails | 0.1 | 4 | Pages | $\ICCI_Bank\Documentation
UTP_ViewCardUsage | UT Plan Review | 1 | OPR | 2012-10-15 | Test Plans | UTP_ViewCardUsage | 0.1 | 5 | Pages | $\ICCI_Bank\Documentation
ITP_Review | Integration Testing | 1 | GR | 2012-10-15 | Test Plans | ITP_Review | 0.1 | 8 | Pages | $\ICCI_Bank\Documentation
SchemeReport | Code Review | 1 | OPR | 2012-10-15 | Code | SchemeReport | 0.1 | 2 | Screens | $\ICCI_Bank\WebContent\SchemeReport.jsp
ApplyForCard | Code Review | 1 | OPR | 2012-10-15 | Code | ApplyForCard | 0.1 | 1 | Screens | $\ICCI_Bank\WebContent\ApplyForCard.jsp
ApproveCard | Code Review | 1 | OPR | 2012-10-15 | Code | ApproveCard | 0.1 | 2 | Screens | $\ICCI_Bank\WebContent\ApproveCard.jsp
Fn-getCustomersForScheme | Code Review | 1 | OPR | 2012-10-10 | Code | Fn-getCustomersForScheme | 0.1 | 3 | TestCases | $\ICCI_Bank\src\com\infy\icci\service\ReportService
FngetBlockedDetails | Code Review | 1 | OPR | 2012-10-16 | Code | FngetBlockedDetails | 0.1 | 3 | TestCases | $\ICCI_Bank\src\com\infy\icci\service\ReportService

## Defects
This is the tracker for the defects that are observed in the course of the projects. The defects are found generally when a review is conducted. Thus, we can say that the outcome of a review is the defects which need to be listed here. In the previous sheet where the reviews are documented we find that the outcome of the review will need to be listed here as defects.
Sr No | Review Name | Submitter Id | Status | Description | Owner Id | Assigned To | Type | Priority | Severity | Injected Stage | Cause | Impact | Action Taken
1 | SchemeReport review | sara_406768 | Solved | When selected a schemeId on the list nothing happen | sara_406768 | sara_406768 | Logic | High | Critical | Coding | Impact Not Analyzed | High | Fixed
2 | ApplyForCard | santiago_406749 | Solved | When a form is submitted with a blank space, then it is fill and resubmitted, ocurrs a error with the random generator | santiago_406749 | santiago_406749 | Invalid Test Case | Low | Major | Coding | Impact Not Analyzed | Low | Fixed
3 | ApproveCard | santiago_406749 | Solved | When a card application is generated, no ocurrs nothing | santiago_406749 | santiago_406749 | Invalid Test Case | High | Critical | Coding | Impact Not Analyzed | High | Fixed
4 | UTP_HomePages | santiago_406749 | Solved | Is not clear the navegation in the home page to approve card page | santiago_406749 | sara_406768 | Detailed Design | Medium | Minor | Integration Testing | Ambiguous Spec | Medium | Fixed
5 | Transaction Statistics | edgardo_406751 | Solved | The dynamic table of commandlinks can not send parameters to the bean method so we we didn't know which link were pressed | edgardo_406751 | edgardo_406751 | Others | Medium | Minor | Coding | Impact Not Analyzed | Medium | Fixed
6 | ApplyForCard | santiago_406749 | Solved | It is not clear where a user can apply for a card, then a new link in login screen is put | santiago_406749 | santiago_406749 | Logic | High | Critical | Integration Testing | Insufficient Informn | High | Fixed
7 | ApproveCard | santiago_406749 | Solved | It is not clear the navigation rule for approve card. So, the Link in this page is changed. | santiago_406749 | santiago_406749 | Incorrect Reqmts | Medium | Critical | Integration Testing | Insufficient Informn | Medium | Fixed
8 | ChooseAgreement | mateo_406767 | Solved | When the customer didn't check the terms and conditions, no appers the correct message. | mateo_406767 | mateo_406767 | User Interface | Medium | Minor | Coding | LessDomainKnowledge | Medium | Fixed
9 | ChooseAgreement | mateo_406767 | Solved | When the customer went to the chooseAgreement page, the schemeId selected didn't appear in the session. | mateo_406767 | mateo_406767 | Logic | High | Critical | Coding | Impact Not Analyzed | High | Fixed
10 | ViewCardUsage | mateo_406767 | Solved | When the customer selected a option (this or previous year) didn't appear the correct list into the month select menu. | mateo_406767 | mateo_406768 | Logic | High | Critical | Coding | Impact Not Analyzed | High | Fixed
11 | ViewCardUsage | mateo_406768 | Solved | Whe the customer selected a option into the radio button options, appeared the selectMenu warning message. | mateo_406767 | mateo_406768 | User Interface | Medium | Minor | Coding | Impact Not Analyzed | Low | Fixed
12 | CardDetails | simon_406769 | Solved | I didn't know how to pass and get attributes by session variable so I get some null pointer exception | simon_406769 | simon_406769 | Logic | High | Critical | Coding | LackofExperience | High | Fixed
13 | ViewCardDetails | simon_406769 | Solved | In the project integration gets some errors because in the service the transfer object didn't has all the attributes set | simon_406769 | simon_406769 | Reusability | Low | Minor | Coding | Impact Not Analyzed | Low | Fixed
14 | CardDetails | simon_406769 | Solved | Assigning a single result to a transfer object gets class cast Exception | simon_406769 | simon_406769 | Logic | Low | Minor | Coding | Impact Not Analyzed | Low | Fixed
15 | CardDetails | simon_406769 | Solved | Persistence error while trying to persist an entity without the proper annotation | simon_406769 | simon_406769 | Consistency | High | Critical | Concept Design | Impact Not Analyzed | High | Fixed
16 | ViewCardDetails | simon_406770 | Solved | Persistence error while trying to persist an entity without the proper annotation | simon_406769 | simon_406769 | Consistency | High | Critical | Concept Design | Impact Not Analyzed | High | Fixed
17 | CardDetails | simon_406770 | Solved | when the user enter the proper card number and pin in the sequence diagram didn't say that there are two navigation forms, with scheme already set and without scheme | simon_406770 | simon_406770 | Detailed Design | Low | Minor | Detailed Design | Impact Not Analyzed | Low | Fixed
18 | Fn-getCustomersForScheme | sara_406768 | Solved | ClassCastException | sara_406768 | sara_406768 | Logic | High | Major | Coding | Err in Existing Pgm | Medium | Fixed
19 | FngetBlockedDetails | sara_406769 | Solved | The query for the "other" reason only select if literaly was 'other' in the data base | sara_406768 | sara_406768 | Logic | Medium | Minor | Coding | Impact Not Analyzed | Medium | Fixed
20 | Approve_Pending_RejectedCardReport | yanny_406750 | Solved | when the user enter the proper Dates did not appear the correct percentage of the cards that were accepted or rejected | yanny_406750 | yanny_406750 | Logic | Medium | Critical | Coding | Impact Not Analyzed | Low | Fixed
21 | Approve_Pending_RejectedCardReport | yanny_406750 | Solved | The validations for each of the fields did not show the correct message or format to let the user | yanny_406750 | yanny_406750 | User Interface | Medium | Minor | Coding | LessDomainKnowledge | Low | Fixed
22 | Approve_Pending_RejectedCardReport | yanny_406750 | Solved | When the user pressed the percentage application approve link, didn't bring the dynamic list of CardNo as links | yanny_406750 | yanny_406750 | Others | High | Critical | Coding | LessDomainKnowledge | High | Fixed
23 | Approve_Pending_RejectedCardReport | yanny_406750 | Solved | It is not very clear the navigation rule when the rejected pecentage is pressed. On the screen shots the navigation shows a different navigation path page which is describe in the requirements. | yanny_406750 | yanny_406750 | Detailed Design | High | Major | Integration Testing | Ambiguous Spec | Medium | Fixed
24 | Payment | andres_406766 | Solved | When the user its going to pay with "full" or "minimum" and how can I add the correct interest rate | andres_406766 | andres_406766 | Logic | Medium | Minor | Coding | Impact Not Analyzed | Medium | Fixed
25 | Payment | andres_406766 | Solved | The backlogs its not clear | andres_406766 | andres_406766 | Documentation | High | Minor | Detailed Design | Insufficient Informn | High | Postponed
26 | Payment | andres_406766 | Solved | The cheackcard its not working properly because i never validate if the card its not in the table | andres_406766 | andres_406766 | Logic | Low | Minor | Coding | Impact Not Analyzed | Low | Fixed
27 | Payment | andres_406766 | Solved | The balance amount it’s the money that you have to pay to the bank and the cardamount its your schemeamount - balanceamount | andres_406766 | andres_406766 | Logic | Low | Minor | Documentation | Impact Not Analyzed | Low | Fixed
28 | Payment | andres_406766 | Solved | Problem with the transferObjects | andres_406766 | andres_406766 | Documentation | Low | Minor | Documentation | Impact Not Analyzed | Low | Fixed
29 | Login | luis_406748 | Solved | User can login with any password | luis_406748 | luis_406748 | Logic | High | Critical | Coding | Impact Not Analyzed | High | Fixed
30 | BlockCard | luis_406748 | Solved | The stored function is not working properly | luis_406748 | luis_406748 | Logic | High | Major | Coding | Impact Not Analyzed | High | Fixed
31 | BlockCard | luis_406748 | Solved | The user can block a card already blocked | luis_406748 | luis_406748 | Logic | High | Major | Coding | Impact Not Analyzed | High | Fixed

## Instructions
INSTRUCTIONS:
1. All the fields in the Review sheet are mandatory except when the Review Type is Audits, and then Artifact Unit,
Artifact Version and Artifact Size are not mandatory.
2. All the fields in Defect sheet are mandatory if defects are to be imported.
3. Enter the serial number on the defect sheet if defects are to be imported.
4. If any value of standard code field is not activated, do not import the excel sheet. Contact PADMIN to activate the values.
5. Importing only Reviews with out any Defects.
Fill Reviews in the Review sheet and leave the Defect sheet empty.
6.Importing Multiple Reviews with Defects.
In case you wish to enter multiple reviews and defects at the same time, then please ensure that the reviews entered should
have at least one defect in the defect sheet. However Reviews with out at least one defect in defect sheet will not be imported.
In this case first import Reviews with at least one Defect and then import Reviews with out any Defects as described in the INTRUCTION 5.

## Codes (hidden)
Acceptance Testing
AT Plan Review
Audits
Code Review
CM Plan Review
Detail Dsgn Review
Document Review
Design Input Review
Design Proposal Revi
Drawing Review
Design Calculations
FE Model Review
FE Report Review
FE Results Review
Model Review
Project Review
Project Specific Too
Release Review
HLD Review
IIN Review
ImpactAnalysisReview
Integration Testing
IT Plan Review
Tst-MastrTstStrgyRvw
Performance Testing
PM Plan Review
Prpsl-ContractReview
Reqmts Spec Review
Tst-TestExecution
ST Plan Review
System Testing
Tst-TestPlanReview
Tst-TestReportReview
Tst-TestScriptReview
UI Review
Unit Testing
UT Plan Review
Warranty
OPR
GR
Code
Design Document
Calculations Doc
Design Proposal
Drawing
FE Model
FE Report
FE Result
Model
Project Specific Too
Install Components
Other Documents
Program Specs
Project Plans
Requirements Specs
Test Plans
Number
Function Points
Install Components
Lines of Code
Pages
Screens
TestCases
Use Cases
Comments
Consistency
Documentation
Design Issues
Concept Design
Detailed Design
Detailing
FEA
Modelling
Func Architecture
Incomplete Reqmts
Incorrect Reqmts
Incomplete Test Case
Invalid Test Case
Logic
Memory management
Naming Conventions
Not a Defect
Others
Performance
Planning
Portability
Redundancy
Reusability
Standards
Storage Structure
Tech Architecture
Testability
TestSetup
Traceability
Unclear Reqmts
User Interface
Version Control
AT Planning
Coding
CM Planning
Detailed Design
Documentation
Concept Design
Detailing
FE Modelling
Integration of the D
Modelling
Post Processing
Report Preparation
Functional Doc
High Level Design
IIN Setup
Impact Analysis
Integration Testing
Intg Test Planning
Tst-MasterTestStrgy
PM Planning
Prpsl-ContractReview
Reqmts Analysis
Tst-DataSetup-Exec
System Test Planning
System Testing
Tst-TestPlanPrep
Tst-TestReportPrep
Tst-ScriptGen-Automn
Tst-ScriptGen-Manual
Unit Testing
Unit Test Planning
Warranty